## Slide 1
ROADMAP · WHO, WHEN, AND HOW WE MEASURE
From one pilot to a national programme.
NOW
To 27 Oct 2026
PILOT
Nov 2026 to mid 2027
SCALE
2027 to 2028
REGION
After a proven pilot
WHO WE
APPROACH
Tech4City judges and mentors
Families from our user testing
IMDA first, for a pilot cohort
SPF Scam Public Education Office and NCPC, through IMDA
One bank or telco, for a paid pilot
Government programme licences: IMDA, SPF, NCPC, MOE
More banks and telcos
One anti-scam agency in a second ASEAN country, starting from our Singapore results
MILESTONE
Final pitch and live demo, 27 Oct 2026
Grant application in by Dec 2026; first call with IMDA now
Pilot cohort and a paid bank or telco pilot by Q1 2027
First government programme licence
Agency dashboard (anonymised) live
Second-market pilot launched with local languages
HOW WE
MEASURE
Drills run end to end on a real phone
Consent checks pass
% who hang up or report in a drill: first vs later
% who finish a drill and come back
Targets set with the partner
Households reached
Cost per household
Still practising after 3 months
Same measures, new language, compared with Singapore
A plan, not commitments: named bodies are outreach targets and no agreements exist yet. In-drill behaviour is our proxy for real-world outcomes; we would ask partners for scam-report data to test that.
Notes: Walk it left to right. Who: we name real bodies we would approach, SPF's Scam Public Education Office with NCPC, and the senior volunteer networks (Project PRAISE, Silver Generation Ambassadors) - say these are targets, not partners. Milestones are dated from the 27 Oct final. Measures: what we can measure ourselves is in-drill behaviour (hang up or report, repeat practice); be upfront that it is a proxy for real scam outcomes, and that we would test it with partner data. Do not state any target number unless it has been agreed with a partner.